## Hoja1
Goals and tasks | Responsible | Deliver | Midterm | Final | Ext
Midtrem Milestones (1.5 mo) | Responsible | Deliver | Midterm | Final | Ext
S1. Design work, UI improvements and landing revamping
Redesign home page, doc site, UI (tabs, submit forms, Admin navigation, ...) | Designer | Design docs
Redefine content for homepage | Team | Design docs
Fix design/UX issues in current app UI | Team | Tested UI
Improve socialcap.app home page | Team | Tested UI
S2. Technical and user documentation and videos
Finish Socialcap white paper (on social-consensus and voting) | Team + Research Assoc. | Whitepaper
Rewrite technical docs with improvement | Team | Tech docs
Create tutorial and videos | Team | Videos
Create documentation site | Team | Doc site online
S3. Payment for Credentials
Review actual code and do cleanup and refactoring | Team | Refactor doc
Review implementation done for Cohort1 | Team | Review doc
Add UI config features | Team | Tested UI
Test alternative cloud-worker implementation for payment | Team | Test cases
Implement payments (browser or cloud-worker) | Team | Tested UI
Implement distribution fees contract/service | Team | Tested Service
Final Milestones (3 mo) | Responsible | Deliver | Midterm | Final | Ext
S4. Migration to MINA Mainnet (dev and devops work)
Mantainance devnet (socialcal.dev on Berkeley) | Team | Devnet running
Mantainance current prod (socialcap.app on Berkeley) | Team | Testnet running
Continuous testing on devnet | Team | Test cases
Migrate current prod (socialcap.app on Mainnet, when ready) | Team | Mainnet running
S5. Devnet + Mainnet Community manager and user support
Train actual support team in new features | Team | Train docs
Give support to users and devs on Socialcap mainnet and devnet | Team
S6. Devnet + Mainnet Infrastructure and operations
Mantain infra for Hetzner servers and additional services | Team
Select stable IPFS provider | Team
S7. Devnet + Mainnet software maintenance
Mantainance devnet (socialcal.dev on Berkeley) | Team | Devnet running
Mantainance current prod (socialcap.app on Berkeley) | Team | Testnet running
Continuous testing on devnet | Team | Test cases
Increase Team with one junior dev for support | Team | New member
Integrate IPFS with selected provider | Team | Tested Service
Support for devnet and mainnet | Team | Support issues
Maintanace and bug fixes | Team | Support issues
S8. Composition of credentials (Socialcap team).
Define credentials std API for integration | Team | Design docs
Implement new field type for Submission form | Team | Tested UI
Define composition proofs into submitted evidence | Team | Design docs
Implement UI and cloud worker service | Team | Tested UI
Testing on devnet | Team | Tested cases
S9. Tokenizing credentials
Analyze custom token contracts | Team | Design docs
Define token params for community | Team | Design docs
Add UI config option for community | Team | Tested UI
Add token ammount per credential to UI | Team | Tested UI
Modify current credential issuance to assign tokens | Team | Tested Service
Testing on devnet | Team | Tested cases
Final Advanced scope milestones (3 mo) | Responsible | Deliver | Midterm | Final | Ext
A1. Batch Voting Implementation
Analyze alternative implementations | Team+ Aerious Lab team | Design docs
Define integration points | Team+ Aerious Lab team | Design docs
Refactor current code to support integration | Team+ Aerious Lab team | Refactored code
Build new Claim voting contract | Team+ Aerious Lab team | Tested Service
Refactor cloud voting dispatches | Team+ Aerious Lab team | Tested Service
Testing on devnet | Team+ Aerious Lab team | Tested cases
A2. MinaNFT Integration
Analyze alternative implementations | Team+ Mikhail Korotkikh | Design docs
Define integration points | Team+ Mikhail Korotkikh | Design docs
Refactor current code to support integration | Team+ Mikhail Korotkikh | Refactored code
Modify current credential issuance to create MINANFT | Team+ Mikhail Korotkikh | Tested Service
Testing on devnet | Team+ Mikhail Korotkikh | Tested cases
A3. Efficient Collections using Protokit
Analyze alternative implementations | Team+ Protokit team | Design docs
Define integration points | Team+ Protokit team | Design docs
Refactor current code to support integration | Team+ Protokit team | Refactored code
Modify current backend to suppor Protokit | Team+ Protokit team | Tested Service
Testing on devnet | Team+ Protokit team | Tested cases
A4. Adding notarized 'Proof Fields' to the Submission Form
Analyze alternative implementations | Team+Rafael Campos | Design docs
Implement Notarizer for Github commits | Rafael Campos | Tested Service
Implement notarizer field type in Submission form | Team+Rafael Campos | Tested UI
Include notarized field in evidence data | Team+Rafael Campos | Tested UI
Testing on devnet | Team+Rafael Campos | Tested cases
A5. Use of zkCloudWorkers (Socialcap team)
Analyze alternative temporary adapter | Team | Design docs
Define integration points | Team | Design docs
Implement temporary cloud worker version | Team | Tested Service
Integrate final version (when zkCloudWorker advances are ready) | Team | Tested Service
Testing on devnet | Team | Tested cases